## Hafren Dyfrdwy
Hafren Dyfrdwy Annual Progress Report Data Table - January 2026
[11 empty] | Current stage of the DWMP study |  |  |  |  | Reporting and review
Level 1 Company | County | Level 2 catchment name | Level 3 catchment name | Current estimated population equivalent (2025) (nr) | Future estimated population growth between 2025 and 2055 (%) | Detailed study planned | Water quality impact study planned | Date of most recent revision of the full plan (incl. previous cycles) | Date of most recent revision of the short-term plan (incl. previous cycles) | Revision required due to performance trend or changes | Strategic context | Current performance | Future performance | Options development | Preferred plan | Draft DWMP | Draft DWMP publication consultation | Final DWMP
HDD | Powys | HDD Teme | Knighton | 2880.3583 | 19.48% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llanfyllin | 1153.6521 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llanfair Caereinion | 984.0338 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Sarn | 204.7459 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Caerhowel | 119.9877 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Forden | 528.0153 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Newtown | 12560.2108 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Clatter | 85.3118 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Kerry | 819.6773 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Montgomery | 1018.6795 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llansilin | 290.8965 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Arddleen And Burgedin | 498.1238 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Bwlch-Y-Fridd | 82.7611 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llangadfan | 520.1763 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llansantffraid - Rbc Works | 885.1525 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Four Crosses | 1391.2684 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llanfechain | 276.1294 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llandyssil | 191.1062 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Pontrobert | 162.2856 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llanwddyn | 154.2533 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Carno | 549.5603 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Tregynon | 641.3802 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Welshpool | 8501.7518 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Bettws Cedewain | 263.2856 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llanidloes | 3854.6638 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Berriew | 385.2045 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llys Rhys Rhysnant | 43.8752 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Meifod | 415.2153 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Pentrefelin | 29.4365 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llandinam | 279.4995 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llangedwyn | 82.3225 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Trewern | 801.738 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Manafon | 52.8339 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Adfa | 158.3671 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Bausley | 458.3539 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Teme | Knucklas | 252.9603 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Trefeglwys | 270.439 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Dolanog | 49.0285 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Pool Quay | 66.0974 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Penybont - Llanerch Emrys | 22.5639 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llangynog | 164.5986 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Castle Caereinion | 370.2677 | 9.029% | Yes Prioritised | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Deytheur | 15.2779 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Llanrhaeadr | 562.9203 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Heniarth | 35.5074 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Penybontfawr | 240.789 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Van | 132.5076 | 9.029% | Yes | Review Underway | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Church Stoke | 867.2938 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Guilsfield | 1292.5245 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028
HDD | Powys | HDD Severn Uplands | Caersws | 1162.9175 | 9.029% | Yes Prioritised | Yes | Mar-23 | Mar-23 | No | Complete January 2026 | In progress | In progress | To commence in Summer 2026 | Scheduled for 2027 | Publication by 01 November 2027 | Open for 12 weeks from 01 November 2027 | By 31 August 2028